## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 3
PROJECT NAME | IMS Mobile App
PROJECT MENTOR (sponsor) | Ms. Lalitha Gutha
TEAM MEMBERS | Abhiram Tilak Potula
Samyak Mishra
Hemanth Sunkireddy
Jakeer Hussain

## Status
15
Mobile interface of IMS IIIT Hyderabad
Ms. Lalitha Gutha, IT office, IIIT H
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21) | [6 empty] | #NAME? | #NAME?
Have an team meet – 1 | Coordination | Everyone | 1 | 2 | Done | The meeting was a mess, we also formulated queries to ask to client | #NAME? | #NAME?
Github Setup | Interfaces | Samyak | 0.3 | 0.15 | Done | Use given link to setup | #NAME? | #NAME?
Client meeting 1 | Requirements | Everyone | 0.5 | 0.75 | Delayed | Discussed project aspects, given task to design UI | #NAME? | #NAME?
Team Meet – 2 | Coordination | All but Abhiram | 1 | 1.5 | Done | Setup figma to design UI, made basic design, split work | #NAME? | #NAME?
Figma Setup | Interfaces | Hemanth | 0.3 | 0.4 | Done | Make team on figma to host the design pages | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
|  |  | Total: | 0 |  |  | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Week 2 (January 22 - January 28) | [6 empty] | #NAME? | #NAME?
Team Meet – 3 | Design | Everyone | 1.5 | 2 | Done | To discuss colour scheme and more design aspects | #NAME? | #NAME?
UI Design – Login Page | Design | Hemanth | 4 | 3 | Done | Make a login page design in figma | #NAME? | #NAME?
UI Design – Dashboard Page | Design | Abhiram | 4 | 4 | Delayed | Make the dashboard and sidebar in figma | #NAME? | #NAME?
UI Design – Profile Page | Design | Jakeer | 4 | 3 | Done | Make the profile/edit page in figma | #NAME? | #NAME?
UI Design – Leave Page | Design | Samyak | 4 | 3 | Done | Make a leave application form in figma | #NAME? | #NAME?
Client meeting 2 | Requirements | Everyone | 0.75 | 1 | Done | To show designs to client, to discuss requirements | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
|  |  | Total: | 16 |  |  | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Week 3 (January 29 - February 4) | [6 empty] | #NAME? | #NAME?
Improvements in UI | Design | Jakeer | 3 | 2 | Done | To improve the designs in the dashboard | #NAME? | #NAME?
Initial draft of requirements | Requirements | Samyak | 2 | 2.5 | Done | Make simple list of features
Team Meet – 4 | Coordination | Everyone | 3 | 1 | Done | Meet to discuss the current progress
Decide on what mobile building tool to use | Coordination | Everyone | 0.5 | 0.75 | Done | Have a group meet to decide what to do in terms of the software to use | #NAME? | #NAME?
Update documentation | Documentation | Abhiram | 1 | 0.25 | Done | Update the MoM and the Excel sheet
Install react in local system | Development | Hemanth | 7 | 10 | Delayed | Install react in arch linux | #NAME? | #NAME?
|  |  | Total: | 16.5
Week 4 (February 5 – February 12 ) | [6 empty] | #NAME? | #NAME?
Improvements in UI – 2 | Design | Jakeer | 2 | 4 | Done | Added bank details and profile page modifications | #NAME? | #NAME?
Client meeting - 3 | Requirements | Everyone | 1 | 0.75 | Done | To show designs to client, to discuss requirements
Team Meet – 5 | Coordination | Everyone | 2 | 3 | Delayed | Now that felicity is over, discuss about future workings and split coding
Make a basic bottom bar | Development | Hemanth | 4 | 8 | Delayed | Make react bottom bar without the icons
|  |  | Total: | 15.75
[7 empty] | #NAME? | #NAME?
Week 5 (February 13 – February 19) | [6 empty] | #NAME? | #NAME?
Navigation and Home Screen | Development | Hemanth | 3 | 2 | Done | Started coding and added basic appearance of Navigation,Home page | #NAME? | #NAME?
Make header which is common to all pages | Development | Everyone | 4 | 4 | Delayed | Added header that is common to all pages | #NAME? | #NAME?
Team Meet – 6 | Coordination | Everyone | 1 | 5 | Done | Discussed about the SRS document and made a list of what to do
Client meeting - 4 | Design | Everyone | 0.5 | 0.3 | Done | Showed basic login page and home page and discussed what to do nxt
|  |  | Total: | 11.3 |  |  | #NAME? | #NAME?
Week 6 (February 20 – February 26) | [6 empty] | #NAME? | #NAME?
Bank Details, Profile Page, Side bar | Development | Everyone | 10 | 5 | Done | Completed My Profile Screens in the app. Working on the API to get real data. | #NAME? | #NAME?
Update Home page and login page appearance | Development | Everyone | 4 | 4 | Done | Completed Login Page and Home Page, Authentication is going on. | #NAME? | #NAME?
Team Meet – 7 | Coordination | Everyone | 4 | 6 | Done | Worked on the Login Page, SRS Document and Test Tracker | #NAME? | #NAME?
Client meeting – 5 | Development | Everyone | 0.5 | 0.6 | Done | Showed initial version of the SRS document and updates on the App. | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
|  |  | Total: | 15.6
[7 empty] | #NAME? | #NAME?
Week 7 (February 26 – March 3) | [6 empty] | #NAME? | #NAME?
Team Meet – 8 | Coordination | Everyone | 4 | 5 | Done | Complete team meet to discuss about further proceedings in frontend | #NAME? | #NAME?
Client meeting – 6 | Interfaces | Everyone | 0.5 | 2 | Cancelled | Due to midsems :( | #NAME? | #NAME?
Authentication using CAS API | Development | Hemanth | 3 | 1 | Done | Try to ask the existing sysadmins about CAS login | #NAME? | #NAME?
Creating API to send data from edit profile. | Preparation | Samyak, Abhiram | 4 | 5 | Done | Create API backend to fetch data, dummy one | #NAME? | #NAME?
Update Leave Application screen on the app. | Development | Jakeer | 3 | 2 | Done | Update frontend leave applications | #NAME? | #NAME?
Team Meet – 9 | Testing | Everyone | 4 | 6 | Done | fill the testing document given by college | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
|  |  | Total: | 21
[7 empty] | #NAME? | #NAME?
Week 8 (March 4 – March 10) | [6 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Put logo in header | Development | Jakeer | 3 | 1 | Done | Try to move the IIITH logo to the top of the stuff | #NAME? | #NAME?
Client meeting – 7 | Coordination | Everyone | 0.5 | 1 | Done | Discuss about features to be dropped and ones to be added | #NAME? | #NAME?
Team Meet – 10 | Coordination | Everyone | 4 | 3 | Delayed | Disucss about R1 and presentations | #NAME? | #NAME?
Improve UI in individual pages | Design | Samyak, Abhiram | 4 | 6 | Done | Try to improve the UI changes proposed in the meet | #NAME? | #NAME?
Try to make some basic form paramaters | Development | Hemanth | 4 | 5 | Done | Send the form parameters to client | #NAME? | #NAME?
Change all docs make a new version | Documentation | Abhiram | 6 | 3 | Done | Make a new version of each and every document | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
|  |  | Total | 19 |  |  | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Week 9 (March 11 – March 18) | [6 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Change all docs make a new version - v2 | Documentation | Abhiram | 3 |  | Done | Change all the documentation and make a new version with changes | #NAME? | #NAME?
Make a presentation | Interfaces | Everyone | 7 |  | Done | Start finding a canva template and start make slides | #NAME? | #NAME?
Discuss on what to say during presentation | Preparation | Everyone | 8 |  | Done | Divide speakers and Discuss with other teams what and when to say | #NAME? | #NAME?
Upgrade all testcases and status before R1 | Testing | Abhiram | 4 |  | Done | Sit and upgrade the status of each testcase | #NAME? | #NAME?
Release 1 | Coordination | Everyone | 4 |  | Done | Present release 1 infornt of Raghu reddy | #NAME? | #NAME?
|  |  | Total | 19 |  |  | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Week 10 (March 18 – March 25) | [6 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Change all docs after R1 submission | Documentation | Hemanth | 5 | 13 | Done | Moodle submission requires all docs after R1, update and submit | #NAME? | #NAME?
Integrate the new API of authentication | Developement | Samyak, Hemanth | 11 | 4 | Done | the client has sent basic auth API, please integrate is as soon as possible | #NAME? | #NAME?
Talk to the client about the API and get her to use our docs | Coordination | Abhiram | 4 | 5 | Done | The client is not really following the api-doc we sent, speak to her personally and get it fixed | #NAME? | #NAME?
create release APK file and put in github releases | Deployment | Jakeer Hussain | 1 | 2 | Done | Make a new tag v1.0 , and put the current apk and aab files there | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
|  |  | Total | 24 |  |  | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Week 11 (March 25 – March 31) | [6 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Integrate the api for fetching profile and Bank details | Development | Samyak | 6 | 7 | Delayed | Use the API given by client to fetch the profile and bank details | #NAME? | #NAME?
Client meeting – 8 | Coordination | Everyone | 0.5 | 1 | done | Discuss how to send pdf through API, session key and how we used two of the API’s | #NAME? | #NAME?
Team Meet – 11 | Coordination | Everyone | 8 | 9 | done | Discuss about implementing new features, integrate the given API’s | #NAME? | #NAME?
Implement notifications and figure out how to send pdf through API | Development | Abhiram, Hemanth | 6 | 7 | done | Implement alerts for tracking status of leave, find a way to send pdf through API | #NAME? | #NAME?
Implement loading page during fetching API | Development | Jakeer | 3 | 4 | done | Create a page that shows a loading circle until the data is fetched from API | #NAME? | #NAME?
|  |  | Total | 28
[7 empty] | #NAME? | #NAME?
Week 12 (April 1 – April 7) | [6 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Start work on Attendance | Development | Abhiram | 4 | 4 | done | Start make UI for the transcript page | #NAME? | #NAME?
Team Meet - 12 | Coordination | Everyone | 3 | 4 | done | Have Teem meet discussing worksplit till R2 | #NAME? | #NAME?
Fill the peer review forms | Coordination | Everyone | 2 | 1 | done | Fill the form given by the course moodle, and write about your satisfaction | #NAME? | #NAME?
Start work on transcipt page | Development | Jakeer | 6 | 4 | done | Start work on the transcript page and make basic UI | #NAME? | #NAME?
|  |  | Total | 13
[7 empty] | #NAME? | #NAME?
Week 13 (April 8 – April 15) | [6 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Make course UI page | Development | Abhiram | 4 | 4 | done | Start make UI for the transcript page | #NAME? | #NAME?
Make API doc finally | Coordination | Hemanth | 2 | 7 | done | Have Teem meet discussing worksplit till R2 | #NAME? | #NAME?
Push for API doc to the client | Coordination | Everyone | 2 | 1 | done | Fill the form given by the course moodle, and write about your satisfaction | #NAME? | #NAME?
Client meeting – 9 | Coordination | Everyone | 6 | 4 | done | Start work on the transcript page and make basic UI | #NAME? | #NAME?
Test changes before R2 | Testing | Samyak | 4 | 2 | done | Test changes so that they meet R2 requirements | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
|  |  | Total | 18 |  |  | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Week 14 (April 16 – April 22) | [6 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
Finalise API nitty-gritties | Interfaces | Samyak, Abhiram | 2 | 1.5 | done | decide exact fields, formats of APIs | #NAME? | #NAME?
Push client to implement API | Coordination | Hemanth | 2 | 2 | done | meet to push for APIs | #NAME? | #NAME?
Figure out file upload to API | Development | Samyak, Hemanth | 3 | 8 | done | explore options for PDF upload | #NAME? | #NAME?
Implement remaining pages | Development | Abhiram, Jakeer | 6 | 10 | done | do work as assigned to all | #NAME? | #NAME?
Update documents | Documentation | Samyak, Abhiram | 3 | 2 | done | reflect changes in project in SRS, Design, Test docs | #NAME? | #NAME?
Client meeting -10 | Coordination | Everyone | 1 | 0.5 | done | meet to show final status | #NAME? | #NAME?
Final Testing | Testing | Everyone | 2 | 2 | done | Test changes so that they meet R2 requirements | #NAME? | #NAME?
Make presentation | Documentation | Hemanth, Jakeer | 3 |  | pending | for final R2 presentation | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
|  |  | Total |  |  |  | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
[7 empty] | #NAME? | #NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?